## week-27
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 27 |  |  | Cross browser controls –issue fix | General | GGR | 2012-07-02 | 2012-07-07 | 35 | Completed
2 | 27 | iTrade |  | iTrade Base 2010 migration issue | General | GGR | 2012-07-04 | 7/04/2012 | 2 | Completed
3 | 27 | iTradeWin |  | iTradewin base 2010 migration issue | General | GGR | 2012-07-04 | 7/04/2012 | 2 | Completed
4 | 27 | iForward |  | iForward-2010 migration-issue fix | General | GGR | 2012-07-05 | 2012-07-05 | 3 | Completed
5 | 27 | iForward |  | iForward perma 2010 migration issue fix | General | GGR | 2012-07-06 | 2012-07-06 | 3 | Completed
1 | 27 |  |  | Cross Browser Controls- fix | General | GGR | 2012-07-02 | 7/02/2012 | 8 | Completed
1 | 27 |  |  | Cross Browser Controls- fix |  | GGR | 2012-07-03 | 7/03/2012 | 8 | Completed
1 | 27 |  |  | Cross Browser Controls- fix | General | GGR | 2012-07-04 | 7/04/2012 | 4
2 | 27 |  |  | iTrade Base 2010 migration issue | General | GGR | 2012-07-04 | 7/04/2012 | 2
3 | 27 |  |  | iTradewin base 2010 migration issue | General | GGR | 2012-07-04 | 7/04/2012 | 2
1 | 27 |  |  | Cross Browser Controls- fix | General | GGR | 2012-07-05 | 2012-07-05 | 2 | Completed
2 | 27 |  |  | iForward-2010 migration-issue fix | General | GGR | 2012-07-05 | 2012-07-05 | 3 | WIP
3 | 27 |  |  | iTradewin base 2010 migration issue fix | General | GGR | 2012-07-05 | 2012-07-05 | 3 | Completed
1 | 27 |  |  | Cross Browser Controls-Report-review&fix | General | GGR | 2012-07-06 | 2012-07-06 | 5 | WIP
2 | 27 | iForward |  | iForward perma 2010 migration issue fix | General | GGR | 2012-07-06 | 2012-07-06 | 3 | completed

## week-28
1 | 28 |  | Cross Browser Controls- fix | General | GGR | 2012-07-09 | 2012-07-09 | 5 | Completed
2 | 28 | iForward | iForward-BLPL-vs 2010 migration | General | GGR | 2012-07-09 | 2012-07-09 | 5 | Completed
1 | 28 | iForward | 2010 migration-issue | General | GGR | 2012-07-02 | 7/02/2012 | 5 | Completed
1 | 28 | iTradewin | Cross Browser Controls-iTradeWinCH integration-Part-1 | General | GGR | 2012-07-11 | 2012-07-11 | 8 | WIP
1 | 28 | iTradewin | Cross Browser Controls-iTradeWinCH integration-Part-2 | General | GGR | 2012-07-12 | 2012-07-12 | 8 | WIP

## week-29
| 29 | iTrade | MultiBoxx | iTradeMB-organization logo issue | Request | GGR | 2012-07-16 | 7/16/2012 | 3 | Completed
| 29 | iComet |  | Grid-issue | Request | GGR | 2012-07-16 | 2012-07-16 | 3 | Completed
| 29 | iTradeCH |  | Confirmation box fix | General | GGR | 2012-07-16 | 2012-07-16 | 2 | Completed
| 29 | iTradewin |  | iTradewinCH-Cross browser Integration | General | GGR | 2012-07-17 | 2012-07-17 | 4 | Completed
| 29 |  |  | iLookup&iFlexgrid issue fix | General | GGR | 2012-07-17 | 2012-07-17 | 3 | Completed
| 29 | iComet |  | iFlexgrid-issue | Requesr | GGR | 2012-07-17 | 2012-07-17 | 1 | Completed
| 29 | iTradeWInCH |  | Cross Browser Controls Integration | General | GGR | 2012-07-18 | 2012-07-18 | 8 | Completed
| 29 | iTrade&iTradeWIn |  | Vs2010 migration-issue | General | GGR | 2012-07-19 | 2012-07-19 | 5 | Completed
| 29 | iComet |  | Grid issue | General | GGR | 2012-07-19 | 2012-07-19 | 1 | WIP
| 29 | iTradewinch |  | Cross browser integration | General | GGR | 2012-07-19 | 2012-07-19 | 2 | Completed
| 29 | Contract |  | Contract Project - Grid issue | issue | GGR | 2012-07-20 | 2012-07-20 | 5 | WIP
| 29 |  |  | Windows authentication-Active directory | General | GGR | 2012-07-20 | 2012-07-20 | 7 | Completed
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 29 | iTrade | MultiBoxx | iTradeMB-organization logo issue | Request | GGR | 2012-07-16 | 2012-07-20 | 3 | Completed
2 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
3 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
4 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
5 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
6 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
7 | 29 |  |  |  |  | GGR | 2012-07-16 | 2012-07-20 |  | Completed
2 | 29 | iComet |  | Grid issue | Request | GGR | 2012-07-16 | 2012-07-20 | 5 | Completed
3 | 29 | iTradeWinCH |  | Cross browser integration | General | GGR | 2012-07-16 | 2012-07-20 | 12 | Completed
4 | 29 | iTradewin |  | Cross browser integration | General | GGR | 2012-07-16 | 2012-07-20 | 2 | Completed
5 | 29 | iControls |  | iLookup&iFlexgrid issue fix | General | GGR | 2012-07-16 | 2012-07-20 | 3 | Completed
6 | 29 | iTrade&iTradeWIn |  | Vs2010 migration-issue | General | GGR | 2012-07-16 | 2012-07-20 | 5 | Completed
7 | 29 | iNova Contract |  | Grid issue | General | GGR | 2012-07-16 | 2012-07-20 | 5 | Completed
8 | 29 |  |  | Windows authentication-Active directory | General | GGR | 2012-07-16 | 2012-07-20 | 7 | Completed

## week-30
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 30 | Dashboard |  | Single Sign on | General | GGR | 2012-07-25 | 2012-07-25 | 8 | WIP
1 | 30 | dashboard |  | Embeded link in postnews | General | GGR | 2012-07-26 | 2012-07-26 | 11 | WIP
2 | 30 | contract |  | Grid issue | Issue | GGR | 2012-07-26 | 2012-07-26 | 8 | WIP
3 | 30 | dashboard |  | SSO-requirement | General | GGR | 2012-07-26 | 2012-07-26 | 2 | Completed
1 | 30 | Dashboard |  | Single Sign on | General | GGR | 2012-07-27 | 2012-07-27 | 8 | WIP
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status
1 | 30 | Dashboard |  | Single Sign on | General | GGR | 2012-07-23 | 2012-07-27 | 16 | WIP
2 | 30 | dashboard |  | Embeded link in postnews | General | GGR | 2012-07-23 | 2012-07-27 | 11 | WIP
3 | 30 | contract |  | Grid issue | Issue | GGR | 2012-07-23 | 2012-07-27 | 8 | WIP
4 | 30 | dashboard |  | SSO-requirement | General | GGR | 2012-07-23 | 2012-07-27 | 2 | Completed

## week-31
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status
1 | 31 | Dashboard |  | Single Sign on | General | GGR | 2012-07-30 | 2012-08-04 | 34 | Completed
2 | 31 | iCadet |  | News Master Changes | Request | GGR | 2012-08-03 | 2012-08-04 | 14 | Completed

## week-32
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status
1 | 32 | iCadet | VSNB | News Master Changes | Request | GGR | 2012-08-13 | 2012-08-16 | 32 | Completed
2 | 32 | iTrade | VSNB | Error Log-issue | Request | GGR | 2012-08-17 | 2012-08-17 | 4 | Completed
3 | 32 | iForward | Perma | Custom Page | Request | GGR | 2012-08-17 | 2012-08-17 | 4 | Completed

## Week-33
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 33 | iCadet | VSNB | News Master Changes | Request | GGR | 2012-08-13 | 2012-08-18 | 17 | Completed
2 | 33 | iNova-Contract | Caravel | Lookup-Request | Request | GGR | 2012-08-14 | 2012-08-14 | 2 | Completed
3 | 33 | iTradewin-CH |  | Cross Browser Controls-Report Review | General | GGR | 2012-08-14 | 2012-08-16 | 8 | Completed
4 | 33 |  |  | Project Management-Requirement | General | GGR | 2012-08-16 | 2012-08-18 | 7.5 | WIP
5 | 33 |  |  | NIIT Training Details -Enquiry | General | GGR | 2012-08-16 | 2012-08-16 | 1 | Completed
6 | 33 | iTrade | MultiBoxx | Code Review | Request | GGR | 2012-08-17 18:17 | 2012-08-17 18:45 | 0.5 | Completed
25
63

## Week-34
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 34 |  |  | Depot-Proforma | General | GGR | 2012-08-21 | 2012-08-21 | 4 | Completed
2 | 34 |  |  | Dynamic RDLC-Feasability Study | General | GGR | 2012-08-21 | 2012-08-21 | 26 | Completed
3 | 34 | iTrade | MultiBoxx | Live Deployment-Assistance | Request | GGR | 2012-08-21 | 2012-08-21 | 1 | Completed
4 | 34 | iNova | PanLlyod | New Vss Configuration | Request | GGR | 2012-08-23 | 2012-08-23 | 1 | Completed

## Week-35
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 35 |  |  | Project Management Requirement | General | GGR | 2012-08-27 | 2012-08-27 | 8 | WIP
2 | 35 | iCadet | VSNB | Problem in Grid on Customer Create Page | General | GGR | 2012-08-28 | 2012-08-28 | 6 | Completed
3 | 35 | iForward | Perma | Issues in vs2010 | Request | GGR | 2012-08-28 | 2012-08-29 | 6 | Completed
4 | 35 | iTrade | VSNB | Tally Forward Service | Request | GGR | 2012-08-29 | 2012-08-30 | 15 | Completed
5 | 35 | iTrade | Perma | Issue in Image Upload | Request | GGR | 2012-08-31 | 2012-08-31 | 4 | Completed
6 | 35 | iNovaContract | Caravel | iNova Contract - iNova Integration | Request | GGR | 2012-08-31 | 2012-09-01 | 5 | Completed

## week-36
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 36 |  |  | Induction Plan | General | GGR | 2012-09-03 | 2012-09-03 | 2.5 | Completed
2 | 36 | iNovaContract | Caravel | Control Width Issue in Grid Search | Request | GGR | 2012-09-03 | 2012-09-03 | 5 | Completed
3 | 36 | iTradeWin | CH | iTradeWin CH - Back to Sales List Issue | Request | GGR | 2012-09-04 | 2012-09-04 | 1 | Completed
4 | 36 | iNovaContract | Caravel | Issue in Grid Search | Issue | GGR | 2012-09-04 | 2012-09-04 | 3 | Completed
5 | 36 | iNovaContract | Caravel | Issue in Grid Expand | Issue | GGR | 2012-09-04 | 2012-09-04 | 2.5 | WIP
6 | 36 | iNova | PanLlyod | iNova: new VSS for Panlloyd | Request | GGR | 2012-09-04 | 2012-09-04 | 2 | Completed
7 | 36 | iNovaContract | Caravel | Issue in Grid Expand | Issue | GGR | 2012-09-05 | 2012-09-05 | 2.5 | WIP
8 | 36 | iNovaContract | Caravel | Issue in user Control | General | GGR | 2012-09-05 | 2012-09-05 | 2.5 | Completed
9 | 36 | iNovaContract | Caravel | Issue in Grid search | Request | GGR | 2012-09-06 | 2012-09-06 | 2 | Completed
10 | 36 |  |  | Project ONYX RFP | General | GGR | 2012-09-06 | 2012-09-06 | 2 | Completed
11 | 36 |  |  | Excel Export | General | GGR | 2012-09-07 | 2012-09-07 | 14 | Completed
12 | 36 | iTradeWin | CH | Web Deployment and Setup | Request | GGR | 2012-09-07 | 2012-09-07 | 1 | Completed

## week-37
S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | 37 |  |  | Induction Demo -Preparation | General | GGR | 2012-09-10 09:30 | 2012-09-12 16:00 | 19.5 | WIP
2 | 37 | iTradeWin | CH | Issue in Sales Grid | Request | GGR | 2012-09-10 14:30 | 2012-09-10 18:15 | 3.75 | Completed
3 | 37 |  |  | Induction iControls-Demo -Preparation | General | GGR | 2012-09-13 09:30 | 2012-09-14 13:00 | 12 | Completed
4 | 37 | iTrade | Perma | Issue in Grid Search | General | GGR | 2012-09-14 14:30 | 2012-09-14 17:30 | 3 | Completed
5 | 37 | iComet |  | MIS Report-issue | Request | GGR | 2012-09-14 17:30 | 2012-09-14 18:40 | 1.1667 | Completed
6 | 37 | iTrade | Perma | Confirmation Box for Depreciation Page | Request | GGR | 2012-09-15 09:30 | 2012-09-15 13:00 | 3.6 | Completed

## Current-Task
IP
|  | S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
|  | 1 | 38 | iTrade | Perma | Confirmation Box for Depreciation Page | Request | GGR | 2012-09-17 10:00 | 2012-09-17 11:30 | 1.5 | WIP | 0
|  | 2 | 38 | General | General | Sql Bulk Copy | General | GGR | 2012-09-17 13:30 | 2012-09-17 16:10 | 2.67 | WIP | 0
|  | 3 | 38 | iTrade | Perma | Confirmation Box for Depreciation Page | Request | GGR | 2012-09-17 16:10 | 2012-09-17 18:30 | 2.33 | Completed | 1
|  | 4 | 38 | General | General | Peoples And Project-Requirement | General | GGR | 2012-09-17 11:30 | 2012-09-17 13:10 | 1.67 | WIP | 0
|  | 5 | 38 | General | General | Sql Bulk Copy | General | GGR | 2012-09-18 09:30 | 2012-09-18 17:30 | 8 | Completed | 1
|  | 6 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 7 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 8 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 9 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 10 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 11 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 12 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 13 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 14 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 15 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 16 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 17 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 18 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 19 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 20 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 21 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 22 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 23 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 24 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | 25 | 38 |  |  |  |  | GGR |  |  | 0 |  | 0
|  | S.No | Wk No | Project | Customer | Task | Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
|  | 1 | 38 | iTrade | Perma | Confirmation Box for Depreciation Page | Request | GGR | 2012-09-17 10:00 | 2012-09-17 18:30 | 3.83 | WIP
|  | 2 | 38 | General | General | Sql Bulk Copy | General | GGR | 2012-09-17 13:30 | 2012-09-18 17:30 | 10.67 | WIP
|  | 3 | 38 | iTrade | Perma | Confirmation Box for Depreciation Page | Request | GGR | 2012-09-17 10:00 | 2012-09-17 18:30 | 3.83 | Completed
|  | 4 | 38 | General | General | Peoples And Project-Requirement | General | GGR | 2012-09-17 11:30 | 2012-09-17 13:10 | 1.67 | WIP
|  | 5 | 38 | General | General | Sql Bulk Copy | General | GGR | 2012-09-17 13:30 | 2012-09-18 17:30 | 10.67 | Completed
|  | 6 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 7 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 8 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 9 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 10 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 11 | 38 |  |  |  |  | GGR | 0 | 0 | 0
|  | 12 | 38 |  |  |  |  | GGR | 0 | 0 | 0
Type
Request
General
Issue
Status
Completed
WIP
On-Hold
Project
iTrade
iTradeWin
iForward
iNova
iNovaContract
iComet
iCadet
iDepo
CES
iDex24
General
iTrade | iTradeWin | iForward | iNova | iNovaContract | iComet | iCadet | iDepo | CES | iDex24 | General
VSNB | CH | BLPL | Caravel | Caravel | BL | VSNB |  | Cronos |  | General
GCR | CTB | Perma | Good Rich
Perma | LM | GLO | DC
CIT |  |  | PanLlyod
MB |  |  | SaiCon
Formulas:
Start Date = MIN(IF([Task]=G4:G20,J4:J20))
End Date = MAX(IF([Task]=G4:G20,K4:K20))

## SHT
2013-02-14 14:43
Project | Total Hours |  | GridDetails
General | 21.01
iTrade | 7.66 |  | Ticket Status
Grand Total | 28.67
Demo Error
IP-LOG
iGTQ
iGTA