## Activity
Consolidated Activities List for 2011
S.No | Activity | Description | Timeline | Risk Involved | Remarks | Prepared By
1 | Customer Care Console | To record and maintain our customers. It is very useful if we have more customers or in SaaS methodlogy. This can be used to maintain their License, Subscription details. |  |  |  | Thiruppathi
2 | Mobile Support | Create mobile applications for the most used and important pages, as well as tracking pages. This may attract more customers |  |  |  | Thiruppathi
3 | Multi tenancy check with all products. | Pay per use is current market trend. If we have Multi tenancy enabled in our application. We can have more small business customers. | 1 month |  |  | Jayakrishnan
4 | iForward Oracle migration. | This is already planned and architecture we built for iForward. We can have customers who are already using oracle in their business. | 15 days |  |  | Jayakrishnan
5 | Installer with patch management. | This is already planned activity. The application deployment time will be reduced once this is achieved. | 1 month |  |  | Jayakrishnan
6 | Product dashboard in landing page for all products. | Entity based dashboard in landing page will help to know the status of important activity in our products. | 1 month |  |  | Jayakrishnan
7 | SOA Session handling revisit. | In iComet, We are started using SOA architecture. If the session is managed by service, We can get good performance in web server. | 1 month |  |  | Jayakrishnan
8 | Revamp the controls as per the requirement given and adding new features. | Controls enhancement will help to reduce our development time. | 2 months |  |  | Jayakrishnan
9 | Javascript obfuscation to be revisited. | We already implemented this is our products. This has to be revisited for other language operating systems. | 5 days |  |  | Jayakrishnan
10 | Clean data services for iComet application. | Data growth will be controlled if we clean un used data in the database. | 5 days |  |  | Jayakrishnan
11 | Session handling revisit in UI framework. | Session is problem for us to implement caching in User Interface. If we store the session data in client machine in the form of JSON. We can reduce the load in web server. | 15 days |  |  | Jayakrishnan
12 | CSS framework for all the products. | If we had a common CSS framework. We can make it a unique User Interface for all of our products and also we can maintain easily. | 15 days |  |  | Jayakrishnan
13 | Animation in UI Elements. | Look and feel will be improved if we have a animated User Interface. | 15 days |  |  | Jayakrishnan
14 | Archiving in iForward. | This is already planned activity. This will be helpful in terms of data growth in database. This has to be considered to all of our products | 5 days |  |  | Jayakrishnan
15 | Common Javascript Library for all the products. | We can maintain easily, If we have common javascript library. Code reusablity also will be achieved. | 15 days |  |  | Jayakrishnan
16 | Single Signon for all products. | Almost we had a same schema in all our products. If we had a common login for all the applications. Customer will be happy to not remembering credentials. | 15 days |  |  | Jayakrishnan
17 | WCF Routing in Service Station. | This has to be implemented in our Service Station tool. If the load is heavy, We can bye pass the service signals to different host. | 1 month |  |  | Jayakrishnan
18 | Licensing web application with automated license generation & payment. | Licensing is our major activity for us. If we have a track the licenses & the payment activities. This tool will help more in terms of product licensing. | 1 month |  |  | Jayakrishnan
19 | Common build machine configuration for UAT & Live build. | We are having build issues in development machines. If we have common build machine for all our products. This will avoid the issues at the of deployment and reduce the delay. | 5 days |  |  | Jayakrishnan
20 | Multi threading in Javascript using web workers. | If we consider this multi threading interms of user interface alone. We can get the user friendly and speedy User Interface in client end. | 15 days |  |  | Jayakrishnan
21 | iAPPMOM revisit. | iAppMOM is main tool for us to know the server status in client end. This has to be enhanced to avoid environment & performance issues in client end. | 2 months |  |  | Jayakrishnan
22 | Knowledge base tool. | This tool will help us to reduce time delay in resolving issues. | 15 days |  |  | Jayakrishnan
23 | iALL tool revisit. | iALL tool is not used by all of us. This has to be revisited. | 15 days |  |  | Jayakrishnan
24 | Planning & Scheduling using MS Project 2010. | If we planned our acvitiy in MS Project 2010. It will be more effective in terms of taking report. | 5 days |  |  | Jayakrishnan
25 | ASP.NET 4.0 training. | This is already planned activity. Training in core knowledge of ASP.net 4.0 will be considered. | 2 months |  |  | Jayakrishnan
26 | DB compare tool. | This tool either can be purchased or development by own. | 1 month |  |  | Jayakrishnan
27 | Testing tool for automation & performance test. | Opensource tools are available. We need try different tools available in market. | 15 days |  |  | Jayakrishnan
28 | Exception handling framework. | Unhandled exceptions are thrown now to server. This has to be handled properly. | 15 days |  |  | Jayakrishnan
29 | UI resolution changes in all products. | User Interface resolution changes need to be considered for different resolutions in client end. | 15 days |  |  | Jayakrishnan
30 | Productwise Windows Gadget. | We can try to build gadget for our product. This will help to avoid to login the application to know some important information regularly. | 10 days |  |  | Jayakrishnan
31 | Induction training kit. | Training kit will be improve our training standard. | 5 days |  |  | Jayakrishnan
32 | Mobile Alert for all projects | Mobile alert service for all the projects | 1 month |  |  | Thanganangai
33 | Dashboard for all projects | Dashboard as the home page for all the projects | 1 month |  |  | Thanganangai
34 | iDocmanV3 implementation | iDocmanV3 implementation for common files and folder management | 10 days |  |  | Thanganangai
35 | Revamp the controls | Add new features | 1 month |  |  | Thanganangai
36 | WCF routing | WCF routing service for iComet | 1 month |  |  | Thanganangai
37 | Oracle compatibility | Create Oracle DB for all the projects | 2 month |  |  | Thanganangai
38 | Patch installer | Create patch installer for all projects | 2 months |  |  | Thanganangai
39 | Browser Compatible architecture | Script & Style changes to run the project in all browsers | 1 month |  |  | Thanganangai
40 | iAppmom integration with installer | Integrate iAppmom with installer | 1 month |  |  | Thanganangai
41 | iAppmom DB monitoring | iAppmom enhancements for DB monitoring, error log & Audit | 1 month |  |  | Thanganangai
42 | 25 iNSync | 25 or more iNSync to be conducted |  |  |  | Thanganangai
43 | Training in HTML5, CSS3 | Training on latest technologies like HTML 5, CSS 3 | 2 months |  |  | Thanganangai
44 | Mobile Report charts | Generating Mobile browser compatible charts for mobile | 1 month |  |  | Vishnu
45 | Database growth and prediction | Track the database growth and predict a trend | 1 month |  |  | Vishnu
46 | Move session data to clientside | Move the data stored in the session to clientside to reduce traffic | 1 month |  |  | Vishnu
47 | Revamp iControls | New features for iControls | 1 month |  |  | Vishnu
48 | Chart control for reports | Display reports as charts | 1 month |  |  | Vishnu
49 | Documentation for all components | Documentation for all components and controls developed by techgroup. | 1 month |  |  | Vishnu
50 | Exporting data to other appications. | Research the possibilty of exporting data to other third party applications which the customer might be already using , eg recent suggestion from Arun Prasad for data export to Tally for accounting . This might be the key for easy adoption of our software at customer end. | 1 month |  |  | Vishnu
51 | SQL Server Analysis Service in Products.? | Research the possibilty and feasibilty of implementing SQL Server Analysis service in products for Datamining for better business planning. | 1 month |  |  | Vishnu
52 | Route all techsupport activity through a KB | All techsupport activities should be sent via a knowlwdge base application which will enable logging of all problems and easy ticket management. | 1 month |  |  | Vishnu

## Project
S.No | Project | S/W Platform | Upgrade Required | Technical Desc | Components Used | Reporting Solution | Other Items | Prepared By