## Reaserch&Development
Research and Development
Date
S.No | Name | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
1 | Controls Cross Browser Implementation | Govindarajan | 2011-12-26 | 2012-03-23 | 568 | WIP

## Tickets
Ticket Status
Sno | Ticket No | Project | Description | Issue Type | Issue Status | Ticket Status | Week | Status | Taken By | Reported Date | Start Date | End Date | Priority | Expected Date of Release | Man Hrs | Closed By | Closed Date | Remarks
1 | ITD 794 | iTrade | iTrade VSNB - issue in mail alerts | Bug | Resolved | Open | 48 | WIP | GGR | 2011-12-02 | 2011-12-02 | 2011-12-05 | HIGH
2 | ICA 795 | iCA | iCadet - issue in loading text with '%' charater in it | Bug | Resolved | Closed | 48 | Completed | TN | 2011-12-02 | 2011-12-02 |  | HIGH
3 | 120 796 | idex120 | Session Time Out - OPM- UAT | Bug | Resolved | Closed | 49 | Completed | TN | 2011-12-05 | 2011-12-05 |  | HIGH
4 | ITD 797 | iTrade | iTrade - Sale release alert query | Request | open | Open | 49 | WIP | VIM | 2011-12-07 | 2011-12-07 |  | HIGH
5 | ITD 798 | iTradeWin | iTradewin CBT Rental screen - review | Request | open | Open | 50 | YTS | VIM | 2011-12-12 |  |  | HIGH
6 | INV 799 | iNova | iNova mail digital signature | Request | open | Open | 50 | YTS | VIM | 2011-12-13 |  |  | HIGH
7 | CON 800 | Contrack | VS crashing while editing RDLC. | Request | open | Open | 50 | YTS | VIM | 2011-12-15 |  |  | HIGH
8 | ITT 801 | iTankTrack | grid upload control - requirement for 2 grids | Request | Resolved | Closed | 51 | Completed | VIM | 2011-12-19 | 2011-12-19 | 2011-12-20 | HIGH
9 | ITT 802 | iTankTrack | Date format & Readonly textbox. | Request | Resolved | Closed | 51 | Completed | VIM | 2011-12-19 | 2011-12-19 | 2011-12-20 | HIGH
10 | ITT 803 | iTankTrack | garbage collection - error | Request | Resolved | Closed | 51 | Completed | SRT | 2011-12-21
11 | ITT 804 | iTankTrack | New Database for Testing | Request | Resolved | Closed | 52 | Completed | TN | 2011-12-27 | 2011-12-27 | 2011-12-27 | HIGH
12 | ITW 805 | iTradeWin | Vss Configuration for Senthilkumar | Request | Resolved | Closed | 52 | Completed | GGR | 2011-12-27 | 2011-12-27 | 2011-12-27 | HIGH
13 | INV 806 | iNova | iNova Build Error | Bug | Resolved | Closed | 52 | Completed | TN | 2011-12-27 | 2011-12-27 | 2011-12-27 | HIGH
14 | ITT 807 | iTankTrack | Service and Setup project configuration | Request | open | Open | 52 | YTS | TN | 2011-12-29

## Project Related Dev
Project related development
S.No | Project | Development Task | Development Type | Assigned To | Start Date | End Date | Total Hours | Status | Remarks
Note on D5: vishnu: New Development,issue, change request,

## Planned Activities
Grand Plan
S.No | Activity Name | Description | Planned Start Date | Assigned to | Remarks

## Project Time Sheet
Project Time Sheet
S.No | Project | Resource | Hours | Remarks
| iCOMET | Thanganangai | 12
| Credit Appraisal | Thanganangai | 3
| Contrack | Vishnu | 1
| iNova | Vishnu | 13
| idex24 | Vishnu | 27
| iTrade | Vishnu | 1
| iTankTrack | Vishnu | 21

## InSync (hidden)
iNsync
S.No | Title | Presented by | Presented on | No of Attendes

## Trainings (hidden)
Training Sessions
S.No | Title | Conducted by | Attended by | Attended on | No of Days

## HW&SW Purchace (hidden)
Hardware and Software purchases
S.No | Purchase | Qty | Purchase Date | Vendor | Ref invoice